|  |  |  | Doc. Com-ITU(12)018 |
| --- | --- | --- | --- |
| Copenhagen, 2-4 April 2012 |  |  |  |
| Date issued: | 4 April 2012 |  |  |
| Source: | Chairman Com-ITU |  |  |
| Subject: | Work programme 2012-2014 |  |  |

N

Password protection required? (Y/N)

Summary:

Work programme for 2011-2014.

Proposal:

For consideration.

Background:

Work Programme Com-ITU 2011-2014

| Subject | Output | Start Date | Target Date | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Preparation for PP-14 | ECP Brief | Q 1 2013 | Q 4 2014 |  |  |
| Preparation for Council 2011 | Exchange of views | Q 3 | October 2011 | Started Sep 2011 Finished Sep 2011 Exchange of views (Sep 2011) |  |
| Preparation for Council 2012 | Exchange of views | Q2 2012 | Q 2 2012 |  |  |
| Preparation for WTSA-12 | ECP Brief | Q 3 2011 | Q 4 2012 | Started May 2011 Timeplan (May 2011) Draft Brief (May 2011) Draft ECP | ECP to be adopted [May 2012 and] September 2012. Brief to be adopted November 2012. |
| Preparation for WCIT-12 | ECP Brief | Q 1 2011 | Q 4 2012 | Started May 2011 Timeplan (May 2011, rev Nov 2011) ”CEPT Agreed” input to CWG WCIT-12 - Sep 2011 - Jan 2012 - April 2012 - Draft Brief (April 2012) Draft ECP (April 2012) | ECP to be adopted [May 2012 and] September 2012. Brief to be adopted November 2012. |
| Preparation for WTPF | Exchange of views | Q 2 2012 | Q 2 2013 |  |  |
| Preparation for TSAG 2012 | Exchange of views | Q 4 2011 | January 2012 | February 2012. Completed February 2012. |  |
|  |  | Q 2 2012 | July 2012 |  |  |
| Preparation for TDAG 2011 | Exchange of views | Q 2 2011 | June 2011 | Completed June 2011. |  |
| Preparation for TDAG 2012 | Exchange of views | Q 2 2012 | Q 2 2012 |  |  |
| Preparation for WTDC 2014 | ECP Brief | Q 1 2013 | Q 2014 |  |  |