| Working Group FM |  |  | FM(12)023 |
| --- | --- | --- | --- |
| 74th Meeting |  |  |  |
| Bern, 23 – 27 April 2012 |  |  |  |
| Date issued: |  |  |  |
| Source: | FM44 |  |  |
| Subject: | FM44 progress report |  |  |
| N Group membership required to read? (Y/N) |  |  |  |
| Summary: |  |  |  |
| During the three meetings and webmeetings of FM44 since WGFM#73, the project team worked on the following areas: - Ka band - Revision of ECC/DEC/(09)02 - ERC/ECC Decisions and Recommendations review - Notification under ECC/DEC/(05)10 - GNSS outdoor pseudolites - Spectrum monitoring of GSO satellites - WI 44_17 on ITU-R issue related to Ku band asymmetry - Review of ERC/ECC Decisions |  |  |  |
| Proposal: |  |  |  |
| With regard to the following issues, WGFM is invited to: - Ka band, ESOMP (FM44#18, Agenda Item #5.3; FM44#19, AI#3.1; FM44#20, AI#5.3): - Note and endorse that the draft ECC Report on ESOMP should be limited to GSO systems and that any request for ESOMP using NGSO space stations should be considered separately under a specific item. - Note that FM44#19 has sent an LS to SE40 related to maritime ESOMPs (see Annex 1). A reply from SE40 containing agreed sharing criteria for was subsequently received. - Note that FM44#20 has sent an LS to TC SES to warn this technical committee of ETSI that the band 21.4-22 GHz currently included in the scope of the draft Harmonised Standard (HS) for ESOMP is outside of the scope of the FM44 work and is not expected to be covered by any CEPT regulatory deliverable (see Annex 2). This LS has been directly sent to ETSI without being first submitted to WGFM as this draft HS was then under the process of approval by correspondence (until 26th March) before being sent to public enquiry. - Comment as necessary the draft ECC Report on ESOMP provided in Annex 3. With regard to this draft Report, the main remaining issue is related to the aeronautical ESOMPs. FM44 aims at submitting the final draft ECC Report to WGFM#75 for approval for public consultation. - Comment as necessary the draft ECC Decision on ESOMP provided in Annex 4. With regard to the notification mechanism (see Decides 2), FM44 did not reach consensus at this stage and would be pleased to receive guidance from WGFM on this issue. Details about the pros and cons are given in Annex 5. It was noted that EFIS could be helpful for administrations to provide information on ESOMP use and to identify frequency bands used by the FS (and hence not available for ESOMPs in their territory). FM44 aims at submitting the final draft ECC Decision to WGFM#75 for approval for public consultation. - Ka band, 17.7-19.7 GHz (FM44#18, A.I.#5.4; FM44#20, AI#5.3): - Note that FM44#20 has sent an LS to SE40 related to studies in the 17.7-19.7 GHz band (see Annex 6). - Revision of ECC/DEC/(09)02 (FM44#18, A.I.#6; FM44#20, AI#6.1): - Endorse the inclusion of the distance protection of the Radio Astronomy sites from MSS uplink transmissions despite FM44 was tasked to revise ECC/DEC/(09)02 on the basis of ECC Report 171. This addition (see Considering f and Decides 4) was unanimously supported by FM44. - Approve for public consultation the draft revision of ECC/DEC/(09)02 (Annex 7). - Notification under ECC/DEC/(05)10 (FM44#18, A.I.#8; FM44#20, AI#8): - Approve and sent, if appropriate, the draft LS to CPG (see Annex 8) related to the notification received by the ECO under ECC/DEC/(05)10, with a request for a 37 cm diameter antenna satellite for ESV, and AI 1.8. of WRC-15. As this agenda item may lead to the revision of RR Resolution 902, this may have an impact on the answer that FM44 should give to the ECO on the notification received. - Spectrum monitoring of GSO satellites (FM44#18, A.I.#9): - Note that FM44 has answered to the LS received from SAT MoU on the spectrum monitoring of GSO satellite as proposed by ITU-BR (see Annex 9), inviting SAT MoU to take into account the BR requests, in particular with respect to the cost that would have to be covered by the ITU in case of use of the monitoring station of Leeheim. - GNSS Outdoor pseudolites (FM44#18, A.I.#4; FM44#20, A.I.#4): - Note the draft ECC Report on GNSS outdoor PL (see Annex 10) and that the final draft is expected to be submitted at WGFM#75 for approval for public consultation. - WI 44_17 on ITU-R issue related to Ku band asymmetry (FM44#20, A.I.#9): - Provide guidance to FM44 if this work item should be considered relevant for CPG only (under the preparation of the Agenda Item 1.6.2 of WRC-15) and closed for FM44. - Review of ERC/ECC Decisions (FM44#20, A.I.#6.2): - Note that if the ECC/DEC/(12)AA is adopted by the ECC in June with the provision of withdrawing ECC Decisions (07)04 and (07)05, FM44 will have no ERC/ECC Decision to review in 2012. Indeed, it should be noted that it has already been agreed that the ERC and ECC Decisions related to the Ka band will be reviewed once the four work items related to this band have been completed. - Chairmanship of FM44: - Nominate a new Chairman for FM44. |  |  |  |
| Background: |  |  |  |
| FM44 had two physical meetings and one webmeeting since WGFM#73. FM44#18 was held in Pozzallo from 16th to 18th November 2011 at the invitation of the Italian administration. The meeting was attended by 27 participants from 9 administrations and 8 organisations (the list of participants is available in document FM44(11)057rev1_Annex 1). The work mainly concentrated on the following issues: - Ka band, uncoordinated FSS Earth stations in the 17.3-17.7 GHz; - Ka band, FSS/FS use of the band 28.8365-28.9485 GHz; - Ka band, ESOMP; - Ka band, 17.7-19.7 GHz band; - Revision of ECC/DEC/(09)02; - Notification under ECC/DEC/(05)10; - Spectrum monitoring of GSO satellites. The Minutes of FM44#18 are available in document FM44(11)057rev1. FM44#19 was held as a Webmeeting on 12th January 2012. The meeting was attended by 19 participants from 8 administrations and 6 organisations (the list of participants is available in document FM44(12)003_Annex 1). The meeting was dedicated to the ESOMP issue. The Minutes of FM44#19 are available in document FM44(12)003. FM44#20 was held in London from 14th to 16th March 2012 at the invitation of the United Kingdom administration. The meeting was attended by 39 participants from 14 administrations and 8 organisations (the list of participants is available in document FM44(12)018_Annex 1). The work mainly concentrated on the following issues: - Outdoor GNSS Pseudolites; - Ka band, ESOMP; - Ka band, 17.7-19.7 GHz band; - Revision of ECC/DEC/(09)02; - Review of ERC/ECC Decisions; - ECC/DEC/(12)AA; - Notification under ECC/DEC/(05)10. The Minutes of FM44#20 are available in document FM44(12)018. The next meeting of FM44 is scheduled on 13th to 15th June in Helsinki at the invitation of the Finish administration. |  |  |  |