PT46(11)031

Date: 28/05/2011 (after-meeting version prepared by ECO) subject to amendments by WGFM and PT chairman.


1. WGFM Active Work Items:

	Responsible  group
	Reference
	Subject
	Scope
	Status
	Remarks
	Start dates

	WG FM
	EFIS/MG_01
	Create new ECC Report
	Provide guidance on the interpretation of ECC/DEC/(01)03 requirements
	In Progress
	WGFM assigned the task to create a new ECC Report providing guidance on the interpretation of the ECC/DEC(01)03 requirements
	01/10/2010

Triggered by France

	WG FM
	EFIS/MG_02
	Further Development of EFIS
	Report on TRA-ECS
	In Progress
	Report delivered by ECO to WGFM in May 2011.

ECO was requested to provide another report in May 2012.
	30/11/2010

Triggered by WGFM

	WG FM
	EFIS/MG_03
	Revision ECC/DEC/(01)03
	Revision;- further development of EFIS
	In Progress
	WGFM agreed to send the revised Decision with changes in annex 2 (application terms) to administration consultation.–
	24/09/2010

Triggered by WGFM

	WG FM
	EFIS/MG_04
	EFIS Software Developments
	Merging ECA DB into EFIS DB; Include EC Decisions in  EFIS and provide search function on basis of the frequency bands
	In Progress
	WGFM instructed the ECO to conduct these software changes in the EFSI DB.
	01/10/2010

Triggered by WGFM

	WG FM
	FM_01
	European Common Allocation Table (ERC Report 25)
	Implementation of ERC Report 25
	In Progress
	WGFM agreed in 02/2011 on the updating process of the ECA Table subject to endorsement by the ECC. A draft revised ERC Report 25 (including the general part) was adopted  for submission to public consultation in 05/2011.
	01/01/2006

Triggered by WGFM

	WG FM
	FM_02
	Civil/Military Forum
	Development of Civil/Military Harmonisation
	In Progress
	"Method of Work for the ECC/WG FM Civil-Military Meeting” was approved by the May 2010 meeting. Date and possible topics for the Civ-Mil meeting in late 2012/early 2013 to be decided at the Oct.  2011 WGFM meeting.
	01/01/1998

Triggered by ECC

	WG FM
	FM_04
	General review of all ECC/ERC Decisions and Recommendation > 5 years old
	Proposals for Decisions and Recommendations to be revised/retain/abrogated as appropriate
	In Progress
	WGFM agreed in 02/2011 on lists with proposals regarding ERC/ECC Decisions and ERC/ECC Recommendations which were submitted to the ECC. An updated list was agreed in May 2011.
	01/01/2006

Triggered by ECC

	WG FM
	FM_07
	WRC-12 Preparation
	Preparation for WRC-12 Agenda Item 1.1 (Deletion of the country names in footnotes of RR Article 5), update of the draft CEPT brief.
	In Progress
	Next version of CEPT Brief expected in June 2011. May 2011 WGFM meeting considered proposals to CPG.
	25/09/2008

Triggered by ECC

	WG FM
	FM_16
	Cognitive Radio Systems (CRS)
	Monitor and investigate CRS, in order to develop a relevant regulatory framework, if needed; collect information on the subject.
	In Progress
	CG CRS of WGFM tasked to consider protection of PMSE on the basis of section D.1 of chapter 11 of ECC Report 159. WGFM agreed to send out via ECO a questionnaire on protection of PMSE in UHF (WSD).
	21/05/2010

Triggered by WGFM

	WG FM
	FM_17
	DVB-H Small Gap Fillers
	Develop a relevant regulatory framework, if needed
	In Progress
	WGFM put the subject on hold in May 2011 in absence of further information from ETSI.
	21/05/2010

Triggered by ETSI SRDoc

	WG FM
	FM_18
	Radio Interface Specifications (RIS)
	Submission of proposals on the RIS template to the WGRA CG RIS
	In Progress
	WGFM will further discuss this subject in October 2011. A number of RIS implementations was delivered and has been formally approved .
	02/11/2009

Triggered by the ECC

	WG FM
	FM_19
	Frequency management during sport events
	Development of an ECC Report
	In Progress
	The outcome of a correspondence group, coordinated by the Russian Federation, was discussed during the May 2011 meeting of WGFM. Work continues in CG and subject will also be discussed during next FM22 meeting.
	04/02/2011

Triggered by Russian Federation

	WG FM
	FM_20
	Equipment sub-classes in accordance with R&TTE Directive
	Consideration of the DECT sub-class 18 based on studies carried out by WGSE (SE PT 7);
	In Progress
	WG FM will consider preliminary results of WG SE in October 2011.
	21/05/2010

Triggered by Germany

	WGFM
	FM_23
	Analyse the merits of  the Authorised Spectrum Access (ASA) concept
	WGFM tasked the CG CRS to discuss this subject and how the concept could possibly be applied.
	In Progress
	The concept is described in FM(11)117Rev1. A first report from CG CRS is expected to WGFM#74 in April 2012.
	17/05/2011

Triggered by ECC / industry contribution

	WGFM
	FM_24
	Revise ECC/DEC/(06)07 on GSMOA
	WGFM tasked WGSE to conduct studies to include 3G in 1920-1980 MHz and 2110-2170 MHz
	In Progress
	Pending agreement of the ECC for ECC/DEC/(06(07  revision.
	17/05/2011

Triggered by WGFM / industry contribution

	WG FM
	FM22_01
	Co-ordination of monitoring in CEPT
	Better co-operation of monitoring within CEPT.
	In Progress
	. Co-ordination on several monitoring subjects is on-going.
	01/01/2004

Triggered by collaboration in FM22

	WG FM
	FM22_05
	BEM compliance measurements
	Development of recommendation on BEM compliance measurements
	In Progress
	The Draft Recommendation was approved for submission to public consultation in 02/2011 (4 months consultation).
	01/01/2009

Triggered by WGFM

	WG FM
	FM22_07
	HF monitoring campaign
	HF monitoring campaign 3 - 30 MHz
	In Progress
	Results under ref="http://www.ero.dk/shortband">www.ero.dk/shortband. Results could be used for the preparation of the next WRC.
	06/02/2009

Triggered by WGFM

	WG FM
	FM22_08
	Review Recommendations 00-08, 05-01 and 02-04
	Review
	In Progress
	More information is provided to WGFM in October 2011. 
	04/02/2011

Triggered by WGFM

	WG FM
	FM22_11
	Monitoring 8 MHz for PT FM46
	(misuse maritime frequencies)
	In progress
	WGFM agreed that FM22 should start this monitoring campaign during the May 2011 meeting. 
	17/05/2011

Triggered by WGFM / FM46

	WG FM
	FM22_12
	Work on an ECC Report on on-site inspections
	Practical considerations to be described in an ECC Report
	In progress
	
	17/05/2011

Triggered by WGFM

	WG FM
	FM38_01
	PMR
	Possible ECC Decisions on PMR harmonisation. The revision of CEPT/ECC/ERC Decisions and Recommendations.
	In Progress
	As result several ECC/ERC REC and ERC/DEC to be withdrawn as per decision of ECC/WGFM#71 and #72.
	01/01/2004

Triggered by ECC

	WG FM
	FM_21
	GSM-R
	1) add a reference to ECC Report 162 in ECC/DEC/(02)05 and ECC/DEC/(04)06 Considerings.
2) Monitor and review situation in 2013/2014 when requested.
	In Progress
	Related ECC Report 162 on practical mechanism to improve compatibility between GSM-R and public mobile networks was adopted by WGSE for publication. 

WGFM decided in May 2011 to submit the 2 revised ECC/DEC for public consultation pending agreement of the ECC..
	01/09/2008

Triggered by WGFM / UIC

	WG FM
	FM_22
	CB Radio
	Examine the possibility to allow FM and AM modulations with 4W and SSB with 12 W (PEP) throughout CEPT
	In Progress
	The new ECC Decision on CB radio has been approved by WGFM for submission to the ECC for final approval..
	21/05/2010

Triggered by ETSI SRDoc

	WG FM
	FM44_11
	FSS operating in 17.3-17.7 GHz 
	Study effective availability of 17.3-17.7 GHz band for uncoord. FSS Earth stations 
	In Progress
	Study whether whole band could be made avail. for unccord. FSS E/s taking into account BSS feeder links. ECC/DECs (05)08, (06)02, (06)03 to be taken into account and potentially revised. 
	24/09/2010

Triggered by WGFM / satellite operators

	WG FM
	FM44_12
	FSS operating in 27.5-29.5 GHz
	Assess possible FSS use without constraint of the 28.8365-28.9485 GHz band
	In Progress
	Assess use of FS in 28.8365-28.9485 GHz, study possibility of uncoordinated E/s., take into account ECC/DECs (06)02, (06)03. WGFM approved a questionnaire on FS usage in the band in 02/2011. A reminder is sent by ECO to those administrations who did not respond yet. Deadline 30 June 2011.
	24/09/2010

Triggered by WGFM / satellite operators in FM44

	WG FM
	FM44_13
	FSS Earth stations on mobile platforms
	Study Ka FSS allocation for use by Earth Stations On Mobile Platforms

(ESOMP)

Develop 1) an ECC Report and 2) an ECC Decision on Earth stations on mobile platforms within the Ka band
	In Progress
	Identify allocation with technical, regulatory and operational restrictions, define technical essential characteristics, define regulatory regime.

ECC to confirm that a new ECC DEC should be developed.

The ECC report should describe the reasoning for the ECC Decision on ESOMP in Ka-Band.
	24/09/2010

Triggered by WGFM / satellite operators in FM44

	WG FM
	FM44_14
	FSS Earth stations operating in 17.7-19.7 GHz
	Study enhanced operations of uncoordinated FSS Earth Stations
	In Progress
	Study whether a regime of exemption from individual licensing could be developed within appropriate subbands

in collaboration with SE19.
	24/09/2010

Triggered by WGFM / satellite operators in FM44

	WG FM
	FM44_15
	Development of a new ECC Recommendation
	Regulatory framework for indoor GNSS pseudolites
	In Progress
	 New draft ECC Recoomendation for indoor pseudolites in 1559-1610 MHz approved for public consultation in May 2011
	04/02/2011

Triggered by WGFM / industry request

	WG FM
	FM44_16
	Develop a new ECC Report on outdoor GNSS pseudolites
	Study possibilities for a regulation for outdoor GNSS pseudolites
	In Progress
	 
	04/02/2011

Triggered by WGFM / industry request

	WGFM
	FM44_17
	Monitoring of the elaboration of the ITU-R Report on the Ku band asymmetry issue, and in particular the potential impact on Region 1 services.
	Work on medium term basis until related ITU-R deliverables are finalised
	In Progress
	Work on CEPT contributions
	17/05/2011

Triggered by WGFM / ITU-R activities

	WGFM
	FM44_18
	Monitoring the revision of the SNG ITU-R Recommendations so as to ensure that these revisions have no impact on exemption from individual licensing and free circulation Decisions.
	Work on medium term basis until related ITU-R deliverables are finalised
	In Progress
	Work on CEPT contributions
	17/05/2011

Triggered by WGFM / ITU-R activities

	WGFM
	FM44_19
	Consolidating the CEPT views on the work on ITU-R Report on terminology to be used for networks using both satellite and terrestrial links
	Work on medium term basis until related ITU-R deliverables are finalised
	In Progress
	Work on CEPT contributions
	17/05/2011

Triggered by WGFM / ITU-R activities

	WG FM
	FM45_01
	Future possibilities for the digitalisation of the sound broadcasting
	Preparation of technical parameters for future digital systems in Band II   Prepare a report on the future possibilities on the future delivery of radio (sound broadcasting services)
	In Progress
	 
	08/02/2008

Triggered by ECC and also ETSI SRDoc

	WG FM
	FM45_03
	Spectrum requirements for PMSE
	Establish and maintain a list of relevant documents and an overview of the relevant on-going PMSE activities in other groups prior to WRC-12. Study the spectrum requirements for wireless microphones after the transition to digital technology which is expected to take place in the next 5-10 years.
	In Progress
	· Study the spectrum requirements for wireless microphones after the transition to digital technology which is expected to take place in the next 5-10 years.

· Review and revise as appropriate the following in the light of the WRC and recent developments in PMSE technology :


- ERC Recommendation 25-10


- ERC Report 042


- ERC Report 038


- ECC Report 002 

Take also into account the CGP AI 1.5 and outcome of WRC’12
	02/07/2008

Triggered by WGFM, one existing ETSI SRDoc, another 6-part ETSI SRDoc is announced by ETSI since considerable time but not delivered yet.

	WG FM
	FM45_04
	Monitor the consequences of practical implementation of conversion of DVB-T allotments into T-DAB assignments in Band III
	ECC Report 116 was developed in response to this item. Some administrations indicated that they are already making such conversions with no particular difficulties FM45 is monitoring information on this.Information to be made available on ECO web site for administrations to check and update for a possible future revision of the Report. 
	In Progress
	
	02/07/2008

Triggered by WGFM / FM45

	WG FM
	FM45_05
	Maintaining the WI95revCO07 and MA02revCo07 plans
	Maintaining the WI95revCO07 and MA02revCO07 Plans - monitor and advise on any action required by the ECO
	In Progress
	WGFM noted the latest version of the document on ‘follow-up activities relating to maintaining the WI95revCO07 and MA02revCO07 Plans’. The MA02revCO07 Plan was updated in December 2009.

Updates are handled by the ECO with information distributed via the website and discussed in FM45.
	02/07/2008

Triggered by ECC

	WG FM
	FM45_07
	SAB/SAP
	SAB/SAP in the UHF and in the band 1452 to 1479.5 MHz
	In Progress
	 Needs to be coordinated with FM50 (FM50 in the lead for the frequency band)
	12/09/2008

	WGFM
	FM45_08
	Other issues
	Review ECC Recommendations and Reports within the scope of FM PT45.
	In progress
	
	18/05/2011

Triggered by WGFM

	WG FM
	FM46_01
	Maritime issues/CEPT preparations for ITU-R WP 5B on relevant maritime issues, excluding WRC-07 mat
	WP 5B addresses issues of a global maritime nature, which impacts on the maritime service. CEPT needs to discuss the proposals of CEPT administrations on maritime items for 5B
	In Progress
	Discussion on the proposals of CEPT administrations on maritime items for WP 5B in order to have a common understanding and a common CEPT approach
	25/09/2008

Triggered by WGFM / ITU-R activities

	WG FM
	FM46_03
	Future licensing of maritime radiocommunications
	Study and consider possible exemption from licensing of maritime equipment, taking into account EU Directives including 2002/20/EC
	In Progress
	 
	25/09/2008

Triggered by WGFM

	WG FM
	FM46_04
	Maritime Issues / IMO  Liaison with IMO on issues of maritime interest
	Preparations and coordination of positions on Agendas for IMO MSC, NAV and COMSAR meetings
	In Progress
	Aim is to create a common understanding with regard to the respective Agenda items and to come to a harmonized CEPT approach.
	20/05/2009

Triggered by WGFM

	WG FM
	FM46_05
	SRC and LRC certification
	1. review of ERC Recommendations T/R 31-4 and T/R 31-05 as they haven’t been reviewed since 1994; 2. investigate on how to structure SRC and LRC training requirements.
	In Progress
	1. Recommendation for the replacement of Rec 31-05 approved in the September 2010 meeting for publication
2. Draft Recommendation or Report.
	20/10/2009

Triggered by WGFM

	WG FM
	FM46_06
	Revision ERC DEC (99)01
	Review ERC DEC (99)01 on the harmonized examination syllabi for the GOC and the ROC and decide on any modifications as found appropriate
	In Progress
	 
	30/11/2009

Triggered by WGFM

	WG FM
	FM46_07
	Co-ordination of actions of CEPT Administrations in the maritime field
	Liaison with relevant CEPT groups and experts within and outside Administrations, e.g. shipping industry, maritime education centers and organizations, which impacts on the maritime service
	In Progress
	Draft guidance (new ECC Recommendation) for Administrations and decide on how to communicate required action. Discussions on developments with regard to ManOverBoardAlertSystems and trying to achieve a common CEPT position.
	01/12/2008

Triggered by WGFM

	WG FM
	FM46_08
	Administrative handling of PLBs
	Investigate and consider national treatment of 406 MHz PLB equipment within CEPT and decide on possibilities for harmonization on use and administrative handling within CEPT
	In Progress
	Discussion on present practices and investigate if CEPT harmonization is feasible.

Establishment of a new ECO information site on administrative handling of PLB.
	20/05/2009

Triggered by WGFM

	WG FM
	FM46_09
	Monitor present and future developments in the field of maritime radiocommunications
	Investigate and consider developments and to decide on the expected impact on future frequency use
	In Progress
	  
	04/02/2011

Triggered by WGFM

	WG FM
	FM46_10
	Review of APP 18 of the Radio Regulations
	Consideration of developments to improve the efficiency of maritime frequency usage
	In Progress
	Draft guidance for Administrations and decide on how to communicate required action.
	04/02/2011

Triggered by WGFM

	WG FM
	FM47_03 (SRDMG)
	Location Tracking Application for Emergency Services (LAES)
	Develop Regulations
	In Progress
	Draft ECC Recommendation was adopted for public consultation. Resolution of the comments is planned during SRD/MG in Sept. 2011.
	02/01/2009

Triggered by ETSI SRDoc

	WG FM
	FM47_04 (SRDMG)
	Location Tracking Applications type 2 (LT2) for person and object tracking and industrial application
	Develop Regulations
	In Progress
	1. ECC Report 167 on practical implementation of registr/coordin mechanism for LT2 systems approved for publication at the WGFM in May 2011.
2. Draft ECC Recommendation adopted for public consultation by WGFM in May 2011. Resolution of the comments is planned during SRD/MG in Sept. 2011.
	01/02/2009

Triggered by ETSI SRDoc

	WG FM
	FM47_05 (SRDMG)
	Location tracking and sensor Applications for automotive and transportation environments (LTA)
	Develop Regulations
	In Progress
	The outcome of the investigations is going to be handled by amending the generic UWB regulation.
	01/02/2009

Triggered by ETSI SRDoc

	WG FM
	FM47_06

(SRD/MG)
	Airborne UWB applications
	Develop Regulations
	In Progress
	Compatibility studies ongoing in SE24
	01/02/2009

Triggered by ETSI SRDoc

	WG FM
	FM47_07 (SRDMG)
	Generic UWB regulation
	Review of Decisions ECC/DEC/(06)04 and ECC/DEC/(06)12
	In Progress
	Draft amended Decision (06)04  with content of (06)12 approved for public consultation in May 2011. DEC(06)12 to be withdrawn after final approval of amended (06)04. Resolution of the comments is planned during SRD/MG in Sept. 2011.
	01/02/2009

Triggered by ETSI SRDoc

	WG FM
	FM48_01
	Spectrum aspects for Broadband-Direct-Air-to-Ground Communications
	Develop Regulations
	In Progress
	Work on spectrum issues concerning Broadband Direct-Air-to-Ground Communications (DA2GC). WGFM approved an LS to WG SE in 02/2011 to initiate studies. WGSE decided to establish SE44. FM48 to reconsider the proposed frequency bands.
	01/10/2010

Triggered by ETSI SRDoc

	WG FM
	SRD/MG_02
	Strategy for SRDs
	A long term strategy for SRDs
	In Progress
	Request to ECO to search in App.3 of Rec.70-03 for national  restrictions. National restrictions list will be forwarded to WGFM to send letter to administrations to lift restrictions if possible.
	01/01/2006

	WG FM
	SRD/MG_03
	SRDs
	Annexes (new or revised) to SRD Recommendation, ERC Decisions and reports.
	In Progress
	Ongoing work on revising ERC/REC 70-03. In 2011, in particular a review of annex 5 including reviewing RTTT, clarify ITS definitions and adding new systems such as WLAM.
	01/01/2000

Triggered by several ETSI SRDoc and related to EC mandate on SRD

	WG FM
	SRD/MG_05
	Review 863-870 MHz
	Identify existing usage and potential for more flexible use of the band
	In Progress
	A WGFM noted the preliminary conclusions and the summary on the reponses to the questionnaire.Final conclusions to be presented to WGFM in Oct. 2011.
	09/01/2009

Triggered by WGFM in reaction to ETSI SRDoc requests on adjacent bands, also related to work under EC mandate on SRD.

	WG FM
	SRD/MG_07
	Future spectrum for UHF SRD, RFID and Smart Metering applications
	Study future spectrum needs
	In Progress
	The ECO report on "Dynamic Evolution of the RFID Market" is published. A CEPT workshop organised by WGFM was held 4-5 April 2011 in Mainz. SRD/MG tasked to identify the need for compatibility studies after the workshop. WGFM has endorsed a roadmap in May 2011. SRD/MG to a) analyse and consolidate the demand b) identify objectives for further analysis and c) further refine the framework for compatibility studies. In parallel, WGFM sent an LS to WGSE to initiate the necessary compatibility and sharing studies in 863-870 MHz, 870-876 /915-921 MHz.
	20/05/2010

Triggered by 3 ETSI SRDoc as well as input from UHF questionnaire and presentations from the workshop. Also related to EC mandate on SRD.

	WG FM
	SRD/MG_09
	MBANS (Medical Body Area Network Systems)
	SRD/MG to identify frequencies and to develop regulation for MBANS
	In Progress
	WGFM has tasked SRD/MG to further investigate the justification and the concept for MBANS. In addition, WGFM has send an LS to WGSE to conduct studies in 4 spectrum options.
	20/05/2010

Triggered by ETSI SRDoc

	WG FM
	SRD/MG_11
	Non-specific SRD ; Multiple Gigabit Wireless Applications in the 60 GHz range
	Possible proposal for changes in the present regulatory framework for the 60 GHz band.
	In Progress
	ERC/REC 70-03 entry in annex 1 under study. ERC/REC for Wideband Data Systems in annex 3 already included for 57-66 GHz.
	01/04/2006

Triggered by ETSI SRdoc and related to EC mandate on SRD

	WG FM
	SRD/MG_13
	Review 1785 and 1800/1805 MHz band edges for radiomicrophone usage
	Review regulation and identify exact conditions for usage at the band edges, also taking into account request to add 1800-1805 MHz for radiomicrophone usage.
	In Progress
	LS from WGFM to WGSE sent in 02/2011 requesting studies to identify exact sharing conditions. Confirmation from WGSE received in May 2011 on studies in SE7. SRD/MG to coordinate with FM45 (FM45 in the lead for PMSE, SRD/MG responsible for REC 70-03 entries). 
	04/02/2011

Triggered by PT1 (1785), Germany (1800-1805), and ETSI SRDoc.

	WG FM
	SRD/MG_14
	Develop common European proposal for contribution to ITU-R WP 1B.
	a) contribution on ITU-R SM.2153 b) contribution on ITU-R PDNR on global and regional harmonised frequencies for SRDs
	In Progress
	Both contributions send to WP1B in May 2011. Pending outcome of WP1B meeting in May 2011, work may continue. Relation to AI 1.22 of WRC’12
	04/02/2011

a) triggered by Germany

b)triggered by supporting European countries (RA-07 multi-country proposal)

	WG FM
	SRD/MG_16
	Study changes in spectrum regulation
	Study implications and benefits if a different spectrum regulation (different to SRD) would be applied to wireless medical implant communications in 401-406 MHz. In addition, SRD/MG is also requested to investigate the implications for other licence-exempt applications which have similar protection requirements.
	In Progress
	Revised ERC/DEC/(01)17 approved for public consultation by WGFM in May 2011
	04/02/2011

Triggered by ETSI (LS)

	WG FM
	SRD/MG_18
	76-77 GHz Surveillance Radars
	Develop regulations
	In Progress
	LS was sent from SRDMG to SE24 to define the exact need for studies in 01/2011. Studies should also take into account sharing situation with adjacent bands as requested in WGFM in 02/2011.
	24/09/2010

Triggered by ETSI SRDoc

	WG FM
	SRD/MG_19
	Industrial wireless SRD applications
	Study future spectrum needs taking into account specific needs such as low latency and high reliability requirements
	In Progress
	WGFM tasked SRD/MG to discuss the subject and provide further guidance to WGSE/SE4 in September 2011. In parallel, WGFM has sent an LS to WGSE to initiate studies.
	04/02/2011

Triggered by ETSI SRDoc

	WG FM
	SRD/MG_21
	Investigate identification of spectrum for WLAM
	Develop regulation
	In Progress
	 Inclusion in ERC/REC 70-03 Annex 5 agreed by WGFM.
	09/09/2010

Triggered by ETSI SRDoc and related to EC mandate

	WGFM
	SRD/MG_22
	PMR446
	Amend ERC/DEC/(98)25
	In progress
	Amend ERC/DEC in line with the LS from ETSI in FM(11)128. Prepare LS to ETSI ERM TG DMR
	16/05/2011

Triggered by Switzerland

	WGFM
	SRD/MG_23
	SRR
	Develop regulation
	In progress
	Develop 2 options on SRR: a) draft revised ECC/DEC/(04)06 or new ECC/DEC for SRR
	18/05/2011

Triggered by ETSI SRDoc and SRR review in RSC/ECC

	WGFM
	SRD/MG_24
	122 GHz
	Review regulation
	In progress
	Possibly identify psd limit to protect EESS(passive)
	Triggered by EC mandate on SRD (in relation to CEPT Report 38)

	WGFM
	SRD/MG_25
	Analyse status 5 GHz WAS/RLAN frequencies
	Study in detail and make a proposal to WGFM
	In progress
	Provide report to WGFM in Oct. 2011
	Triggered by WGFM

	WGFM
	SRD/MG
	169 MHz
	Review as described under the new EC mandate on 169 MHz
	In progress
	WGFM adopted in a first step the 169 questionnaire to industry and administrations in May 2011
	Triggered by new mandate on 169 MHz from the EC.

	WGFM
	FM49_01
	Broadband PPDR
	Identify spectrum for future BB-PPDR
	In progress
	
	16/05/2011

Triggered by ETSI SRDoc

	WGFM
	FM50_01
	Investigate future usage in 1452-1492 MHz
	Develop regulations for future usage in the band 
	In progress
	See also WI45_07.
	16/05/2011

Triggered by ECC/ industry request. PMSE usage in the band : also included in one ETSI SRDoc 


2. WGFM finalised work items:
	Responsible  group
	Reference
	Subject
	Scope
	Status
	Remarks
	End dates

	WG FM
	FM22_03
	Monitoring campaign on SRD in 863-870 MHz
	The campaign aims to collect information to assess the level of utilisation in the band 863-870 MHz
	Finalised
	3rd phase of the monitoring campaign. A report was provided to WGFM, SRD/MG, SE24 and ETSI ERM STF411.
	May 2011



	WG FM
	FM22_09
	Interference to the aeronautical services
	Report about interference situation towards the aeronautical services
	Finalised
	WGFM approved in 02/2011 a questionnaire to administrations to identify the differences in statistics and reporting. Replies on the Questionnaire on statistics and trends for interferences to ARNS presented and delivered to EuroControl. In May 2011.
	May 2011



	WG FM
	FM22_10
	Monitoring 6 MHz for PT FM46
	(misuse maritime frequencies)
	Finalised
	 Report was sent to FM46. ECO Circular Letter sent out via list D and WGFM list. 
	May 2011



	WG FM
	FM38_03
	Public Protection and Disaster Relief (PPDR)
	Future PPDR spectrum use
	Finalised
	 Work on PPDR transferred to new PT FM49.
	May 2011

	WG FM
	FM44_03
	GNSS repeaters
	Develop a report for a regulatory framework for GNSS repeaters
	Finalized
	WGFM approved ECC Report 145. ECC Recommendation (10)02 on a Regulatory framework for GNSS Repeaters published on Oct 10 
	Oct. 2010



	WG FM
	FM44_04
	Use of the frequency bands 27.5-30/17.3-20.2 GHz for satellite networks
	Develop a Report on the Use of the frequency bands 27.5-30/17.3-20.2 GHz for satellite networks
	Finalized
	ECC Report 152 on the use of the frequency bands 27.5-30 GHz and 17.3-20.2 GHz by satellite networks published on Oct 10
	Oct. 2010

	WG FM
	FM44_07
	Protection of EESS in the band 1400-1427 MHz.
	Develop an ECC Decision
	Finalized
	ECC/DEC/(11)01 published in March 2011.
	March 2011

	WG FM
	FM44_08
	Protection of EESS in the band 10.6-10.68 GHz
	Develop an ECC Decision
	Finalized
	ECC Decision (10)01 on sharing between the fixed service, mobile service and the Earth exploration satellite service in the band 10.6-10.68 GHz published in 11/2010
	March 2011

	WG FM
	FM44_09
	Protection of EESS in the band 31.3-31.5 GHz
	Develop an ECC Decision
	Finalized
	ECC Decision (10)02 on protection of EESS in the band 31.3-31.5 GHz published in 11/2010
	March 2011

	WG FM
	FM44_10
	GNSS Pseudolites
	Develop an ECC Report on a regulatory framework for indoor GNSS pseudolites
	Finalised
	ECC Report 168 approved for publication in May 2011
	May 2011

	WG FM
	FM45_02
	Existing and possible future use in the L-Band 1452-1492 MHz
	Assess the existing and possible future usage of the L-Band by means of FM45 questionnaire.
	Finalized
	Results delivered to WGFM in 02/2011.WGFM submitted results to ECC including a proposal on purpose and organisation of the future work
	Feb. 2011



	WG FM
	FM45_06
	DRM
	Deployment of DRM
	Finalized
	Revised version of ECC Report 117 ‘Managing the transition to digital sound broadcasting in the frequency bands below 80 MHz’ published in 10/2010
	Oct. 2010

	WG FM
	FM46_02
	Impact of EU Directives, regulations and decisions on maritime issues
	Review relevant EU legislation in order to be aware of consequences for telecommunications. Advise WGFM on way forward.
	Finalized
	Nothing to report at the present time. 
	March 2011

	WG FM
	FM47_01
	EC Mandate on UWB (Report B)
	Develop a report 
	Finalized
	CEPT Report 34 adopted by ECC in October 2009
	Oct. 2009

	WG FM
	FM47_02
	EC Mandate on SRR
	Develop a report
	Finalized
	CEPT Report 36 and 37 adopted by ECC in June 2010
	June 2010

	WG FM
	JPT BWA_05
	Broadband Wireless Access 
	ECC Decision (07)02 on BWA, ECC Recommendation (06)04 on BFWA, CEPT Report 015, Questionnaire on BFWA at 5.8 GHz
	Finalized
	All work items have been finalized. WG FM decided to close JPT BWA if WG SE agrees.
	May 2008

	WG FM
	SRD/MG_04
	Intelligent Transport Systems in the 5GHz and 63GHz bands
	Develop regulation
	Finalized
	EC DEC, ECC DEC and ECC REC in place for 5.9 GHz ITS, ECC DEC, entry in ERC REC 70-03 in place. Adding to EC DEC on SRD for 63 GHz covered in CEPT Report 38 but under RTTT and w/o using term and ITS definition to avoid unnecessary restrictions.
	Feb 2010

	WG FM
	SRD/MG_06
	Use of the 862-863 MHz band
	Investigate the use of the 862-863 MHz band for SRDs
	Finalized
	WG FM considered the result of a questionnaire on the use of the 862-863 MHz band and decided not to designate the band for SRDs at the moment
	May 2010

	WG FM
	SRD/MG_08
	Fourth update of the EC SRD Decision
	Regular update of the EC SRD Decision
	Finalized
	CEPT Report 38 published in March 2011
	March 2011

	WG FM
	SRD/MG_10
	Low Power Active Medical Implants
	Regulation for the LP-AMI in 2483.5-2500 MHz band
	Finalized
	WGFM approved revised annex 12 of ERC/REC 70-03 in 02/2011
	Feb. 2011

	WG FM
	SRD/MG_15
	Level Probing Radar (LPR)
	Develop regulation
	Finalized
	ECC/DEC for LPR published in 03/2011
	March 2011

	WG FM
	SRD/MG_17
	Study implementation GPR/WPR
	Study national implementation challenges regarding GPR/WPR (Ground and Wall Probing Radar)
	Finalized
	WGFM received questionnaire and endorsed the ECO summary on the responses received. No follow-on action.
	May 2011

	WG FM
	SRD/MG_20
	Progress work on RIS templates for SRD applications
	Develop RIS template for annex 1 of ERC/REC 70-03
	Finalized
	 WGFM decided to stop this work in May 2011. No sufficient support and value seen by administrations.
	May 2011



