## Sheet1
Nb id | ETSI technical body | ETSI project number | procedure | Class with Srdoc, LS, NWI, officials, structure, ToR, etc. | WI Ref & short title | Current status | Achieved date | Version nb | NEXT Status | Target date | PUB plan | As version | ECC Groups | ECC Action | Comment
1 | JTFEA | JTFEA-2 |  | EN | (EN 300 676-2) REN/ERM-JTFEA-007 HS for ground-based VHF hand-held, mobile and fixed radio tx, rx and trx for VHF AMS using AM | Delivery to the EC | 2011-09-05 | 1.5.1
2 | JTFEA | JTFEA-6.1 |  | EN | (EN 301 842-5) DEN/ERM-JTFEA-029-5 Harmonized EN for ground-based VDL Mode 4 equipment | Start of work | 2010-03-24 | ? | Early draft | 2012-01-31 | 2012-12-01 | 1.1.1
3 | JTFEA | JTFEA-5 |  | EN | (EN 303 213-5-2) DEN/ERM-JTFEA-005-5-2 Advanced Surface Movement Guidance and Control System (A-SMGCS); Part 5: Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive for multilateration equipment; Sub-part 2: reference and vehicle transmitters | Early draft | 2011-11-16 | 0.0.8 | Stable draft | 2011-12-30 | 2013-05-19 | 1.1.1 | WG SE21 |  | Rec. 74-01
4 | JTFEA | JTFEA-5 |  | EN | (EN 303 213-6-1) DEN/ERM-JTFEA-005-6 Harmonized EN for Advanced Surface Movement Guidance and Control System (A-SMGCS); Part 6 for deployed surface movement radar sensors; sub-part 1: sensors using pulsed signals and transmitting power up to 100 kW | Delivery to the EC | 2011-09-26 | 1.1.1
5 | JTFEA | JTFEA-6 |  | EN | (EN 301 841-3) DEN/ERM-JTFEA-006 VHF air-ground Digital Link (VDL) Mode 2; Part 3: Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive | Delivery to the EC | 2011-11-08 | 1.1.1
6 | JTFEA | JTFEA-6 |  | EN | (EN 301 841-3) DEN/ERM-JTFEA-010 VHF air-ground Digital Link (VDL) Mode 2; Technical characteristics and methods of measurement for ground-based equipment; Part 3: Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive | TB adoption of WI | 2011-11-25 | ? | Start of work | 2011-11-25 | 2012-06-14 | 1.1.1
7 | JTFEA | JTFEA-7 |  | EN | (EN 303 084) DEN/ERM-JTFEA-015 Ground Based Augmentation System (GBAS) VHF ground-air Data Broadcast (VDB); Technical characteristics and methods of measurement for ground-based equipment; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive | Early draft | 2012-01-17 | 0.0.1 | Stable draft | 2012-03-19 | 2013-05-13 | 1.1.1
8 | ATTM | ATTM |  | EN | (EN 302 217-2-2) REN/ATTM-04018 PP FRS - HEN essential req. art. 3.2 R&TTE, co-ordinated freq. bands | Stable draft | 2012-01-31 | 1.0.0 | WG approval | 2012-05-31 | 2013-05-16 |  | SE19
9 | ATTM | ATTM |  | EN | (EN 302 217-2-2) REN/ATTM-04019 PP FRS - HEN essential req. art. 3.2 R&TTE, co-ordinated freq. bands | Stable draft | 2012-01-31 | 1.0.0 | Final draft for approval | 2012-04-30 | 2012-09-04 | 2.2.1 | SE19
10 | MSG | MSG |  | EN | (EN 301 502) REN/MSG-0006 EN 301 502 v.10.2.1 | Start of Public Enquiry | 2012-01-30 | 10.1.1 | End of Public Enquiry | 2012-05-29 | 2012-07-03 | 10.2.1 | SE7
11 | MSG | MSG |  | EN | (EN 300 609-4) PWI_MSG_20110921_1_v1 GSM Repeater | Start of Public Enquiry | 2012-01-18 | 10.1.1 | End of Public Enquiry | 2012-05-17 | 2012-11-19 | 10.2.1 | SE7
12 | BRAN | BRAN |  | EN | (EN 302 774) REN/BRAN-0060007 HS BWA Base Stations 3.4-3.8 GHz | Delivery to the EC | 2012-02-21 | 1.2.1 | End of OAP | 2012-02-15 | 2012-02-29 | 1.2.1 | SE19, ECC-PT1
13 | TFES | TFES-8 |  | EN | (EN 301 908-4) REN/MSG-TFES-007-4 Harmonized EN for IMT-2000, CDMA Multi-Carrier (cdma2000) and Evolved CDMA Multi-Carrier Ultra Mobile Broadband (UMB) (UE) | Delivery to the EC | 2011-09-19 | 5.2.1 |  |  |  |  | ECC PT1
14 | TFES | TFES-8 |  | EN | (EN 301 908-5) REN/MSG-TFES-007-5 Harmonized EN for IMT-2000, CDMA Multi-Carrier (cdma2000) and Evolved CDMA Multi-Carrier Ultra Mobile Broadband (UMB) (BS) | Delivery to the EC | 2011-09-19 | 5.2.1 |  |  |  |  | ECC PT1
15 | TFES | TFES-10 |  | EN | (EN 301 908-21) DEN/MSG-TFES-009-21 Harmonized EN for IMT-2000 OFDMA TDD WMAN (Mobile WiMAX) FDD User Equipment (UE) | Delivery to the EC | 2011-09-19 | 5.2.1 |  |  |  |  | ECC PT1
16 | TFES | TFES-10 |  | EN | (EN 301 908-22) DEN/MSG-TFES-009-22 Harmonized EN for IMT-2000 OFDMA TDD WMAN (Mobile WiMAX) FDD Base Stations (BS) | Delivery to the EC | 2011-09-19 | 5.2.1 |  |  |  |  | ECC PT1
17 | TFES | TFES- |  | EN | (EN 301 908-1) REN/MSG-TFES-010-01 IMT cellular networks; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 1: Introduction and common requirements | TB adoption of WI | 2011-11-08 | ? | Start of work | 2011-11-08 | 2013-04-17 | 6.2.1 | ECC PT1
18 | TFES | TFES- |  | EN | (EN 301 908-2) REN/MSG-TFES-010-02 IIMT cellular networks; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 2: CDMA Direct Spread (UTRA FDD) User Equipment (UE) | TB adoption of WI | 2011-11-08 | ? | Start of work | 2011-11-08 | 2014-01-01 | 6.2.1 | ECC PT1
19 | TFES | TFES- |  | EN | (EN 301 908-3) REN/MSG-TFES-010-03 IMT cellular networks; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive Part 3: CDMA Direct Spread (UTRA FDD) Base Stations (BS) | TB adoption of WI | 2011-11-08 | ? | Start of work | 2011-11-08 | 2013-10-03 | 6.2.1 | ECC PT1
20 | TFES | TFES- |  | EN | (EN 301 908-11) REN/MSG-TFES-010-11 IMT cellular networks; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 11: CDMA Direct Spread (UTRA FDD) (Repeaters) | Early draft | 2011-12-12 | 0.0.1 | Stable draft | 2011-12-16 | 2013-04-17 | 6.2.1 | ECC PT1
21 | TFES | TFES- |  | EN | (EN 301 908-13) REN/MSG-TFES-010-13 IMT cellular networks; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 13: Evolved Universal Terrestrial Radio Access (E-UTRA) User Equipment (UE) | TB adoption of WI | 2011-11-08 | ? | Start of work | 2011-11-08 | 2014-01-01 | 6.2.1 | ECC PT1
22 | TFES | TFES- |  | EN | (EN 301 908-14) REN/MSG-TFES-010-14 IMT cellular networks Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive Evolved Universal Terrestrial Radio Access (E-UTRA) Base Stations (BS) | TB adoption of WI | 2011-11-08 | ? | Start of work | 2011-11-08 | 2013-10-03 | 6.2.1 | ECC PT1
23 | TFES | TFES- |  | EN | (EN 301 908-15) REN/MSG-TFES-010-15 IMT cellular networks; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 15: Evolved Universal Terrestrial Radio Access (E-UTRA FDD) (Repeaters) | Early draft | 2011-12-12 | 0.0.1 | Stable draft | 2011-12-16 | 2013-04-17 | 6.2.1 | ECC PT1
24 | TFES | TFES- |  | EN | (EN 301 908-19) REN/MSG-TFES-010-19 IMT cellular networks; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 19: OFDMA TDD WMAN (Mobile WiMAX) TDD User Equipment (UE) | TB adoption of WI | 2011-11-08 | ? | Start of work | 2011-11-08 | 2013-12-30 | 6.2.1 | ECC PT1
25 | TFES | TFES- |  | EN | (EN 301 908-20) REN/MSG-TFES-010-20 IMT cellular networks; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 20: OFDMA TDD WMAN (Mobile WiMAX) TDD Base Stations (BS) | TB adoption of WI | 2011-11-08 | ? | Start of work | 2011-11-08 | 2014-01-02 | 6.2.1 | ECC PT1
26 | TGDMR | TGDMR-302 |  | EN | (EN 300 296-2) REN/ERM-TGDMR-303 Land Mobile Service; Radio equipment using integral antennas intended primarily for analogue speech; Part 2: Technical characteristics and methods of measurement | TB adoption of WI | 2011-12-08 | ? | Start of work | 2011-12-08 | 2012-10-13 | 1.4.1 | SE7
27 | TGDMR | TGDMR-2.1 |  | EN | (EN 300 433-2) REN/ERM-TGDMR-266-2 Citizens' Band (CB) radio equipment | Delivery to the EC | 2011-07-21 | 1.3.1 |  |  |  |  | SE7
28 | TG37 | TG37-4.1 |  | EN | (EN 302 571) REN/ERM-TG37-009 ITS radiocommunications equipment operating in the 5 855 MHz to 5 925 MHz frequency band | Early draft | 2011-10-26 | 1.2.2 | Final draft for approval | 2012-02-01 | 2013-03-01 | 1.2.1 | SE24, SRD-MG
29 | TG26 | TG26-4.5 |  | EN | (EN 302 885-2) DEN/ERM-TG26-088-2 Portable Very High Frequency (VHF) radiotelephone equipment for the maritime mobile service operating in the VHF bands with integrated handheld class D DSC; Part 2 | Delivery to the EC | 2011-09-26 | 1.1.1 |  |  |  |  | Forum Group Maritime
30 | TG26 | TG26-8 |  | EN | (EN 302 961-2) DEN/ERM-TG26-099-2 Maritime Personal Homing Beacon intended for use on the frequency 121,5 MHz for airborne search and rescue purposes; Part 2: Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive | Start of Public Enquiry | 2011-12-21 | 1.0.0 | End of Public Enquiry | 2012-04-19 | 2012-02-28 | 1.1.1 | Forum Group Maritime
31 | SES | SES |  |  | (EN 301 681) REN/SES-00320 HS for (Geo) Mobile Earth Stations 1,5/1,6 GHz | Delivery to the EC | 2011-11-24 | 1.4.1 |  |  |  |  | SE40, FM44
32 | TG28 | TG28-1 | adopt | NWI | (EN 300 330-2) REN/ERM-TG28- Short Range Devices (SRD); Radio equipment in the frequency range 9 kHz to 25 MHz and inductive loop systems in the frequency range 9 kHz to 30 MHz; Part 2: Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive | TB adoption of WI | [6 empty] | SE24, SRD-MG
33 | TG28 | TG28-2.3 |  | EN | (EN 300 220-2) REN/ERM-TG28-0441 Short Range Devices (SRD); Radio equipment to be used in the 25 MHz to 1 000 MHz frequency range with power levels ranging up to 500 mW; Part 2: Harmonized EN covering essential requirements under article 3.2 of the R&TTE Directive | Start of OAP | 2012-01-09 | 2.4.1 | End of OAP | 2012-05-08 | 2012-05-22 | 2.4.1 | SE24, SRD-MG
34 | TG28 | TG28-4.2 |  | EN | (EN 305 550-2) DEN/ERM-TG28-0421-2 Non-specific SRDs in the 40 GHz to 246 GHz | Delivery to the EC | 2011-07-21 | 1.1.1 |  |  |  |  | SE24, SRD-MG
35 | TG30 | TG30-2 | NV | EN | (EN 301 559-2) DEN/ERM-TG30-301 Low Power Active Medical Implants (LP-AMI) and related peripheral devices operating in the 2483.5 to 2500 MHz bands; Part 2: Harmonized EN covering essential requirements of article 3.2 of the R&TTE Directive | Start of TB review of PE comments | 2011-11-10 | 1.1.1 | Start of TB approval process | 2012-01-05 | 2012-05-14 |  | SE24, SRD-MG
36 | TG34 | TG34-6 |  | EN | (EN 302 208-2) REN/ERM-TG34-013 HS for 2 W RFID at UHF | Delivery to the EC | [6 empty] | SE24, SRD-MG
37 | TGUWB | TGUWB-15 |  | EN | (EN 302 065-1)REN/ERM-TGUWB-016 SRD using UWB technology for communications purposes; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 1: Common technical requirements | Early draft | 2011-07-20 | 0.0.1 | Stable draft | 2011-10-15 | 2011-10-04 | 1.3.1 | SE24, SRD-MG | work was on hold --> now EC mandate to ECC to update EC UWB Dec --> work will be resheduled
38 | TGUWB | TGUWB-16 |  | EN | (EN 302 065-2) DEN/ERM-TGUWB-017 SRD using UWB for communications purposes; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 2: Requirements for UWB location tracking | Early draft | 2011-07-19 | 0.0.1 | Stable draft | 2011-08-15 | 2011-10-04 | 1.1.1 | SE24, SRD-MG | work was on hold --> now EC mandate to ECC to update EC UWB Dec --> work will be resheduled
39 | TGUWB | TGUWB-5 |  | EN | (EN 302 065-3) DEN/ERM-TGUWB-018 SRDs using Ultra Wide Band technology (UWB) for communications purposes; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive; Part 3: Requirements for UWB devices for road and rail vehicles | Start of work | 2010-11-08 | ? | Early draft | 2011-03-15 | 2012-05-30 | 1.1.1 | SE24, SRD-MG | work was on hold --> now EC mandate to ECC to update EC UWB Dec --> work will be resheduled
40 | TGSRR | TGSRR-4 |  | EN | (EN 301 091-2) REN/ERM-TGSRR-060 Radar equipment operating in the 76 GHz to 77 GHz range; Part 2: Harmonized EN covering essential requirements of article 3.2 of the R&TTE Directive | TB adoption of WI | 2011-12-08 | ? | Start of work | 2011-12-08 | 2013-03-30 | 1.4.1 | SE24, SRD-MG
41 | TGSRR | TGSRR-5 |  | EN | (EN 303 057-2) DEN/ERM-TGSRR-054-2 24 GHz WLAM | Start of work | 2010-03-26 | ? | WG approval | 2012-05-16 | 2013-05-20 | 1.1.1 | SE24, SRD-MG
42 | TGSRR | TGSRR-6 |  | EN | (EN 302 858-2) DEN/ERM-TGSRR-051-2 EN for NB SRR @ 24 to 24,250 GHz band | Delivery to the EC | 2011-07-21 | 1.2.1 |  |  |  |  | SE24, SRD-MG
43 | TGSRR | TGSRR-7 |  | EN | (EN 302 288-2) REN/ERM-TGSRR-056-2 24 GHz Short Range Radar | Start of Vote | 2012-01-18 | 1.6.1 | End of Vote | 2012-03-19 | 2012-04-02 | 1.6.1 | SE24, SRD-MG
44 | TG11 | TG11-10 | adopt | NWI | Revision of EN 300 328 V1.8.1 (REN/ERM-TG11-010) Wideband transmission systems; Data transmission equipment operating in the 2,4 GHz ISM band and using wide band modulation techniques; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive | TB adoption of WI | [6 empty] | SE24, SRD-MG | work will start after national vote of version 1.8.1
45 | TG11 | TG11 |  | EN | (EN 301 893) REN/BRAN-0060006 HS for 5 GHz RLANs | Delivery to the EC | 2011-11-15 | 1.6.1 |  |  |  |  | SE24, SRD-MG
46 | TG11 | TG11 |  | EN | (EN 301 893) REN/BRAN-0060009 HS for 5 GHz RLANs | Start of OAP | 2012-01-31 | 1.7.0 | End of OAP | 2012-05-30 | 2012-06-13 | 1.7.1 | SE24, SRD-MG
47 | TG11 | TG11 |  | EN | (EN 302 567) REN/BRAN-0060008 60 GHz Multiple-Gigabit WAS/RLAN Systems; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive | Delivery to the EC | 2012-01-16 | 1.2.1 |  |  |  |  | SE19, SE24, SRD.MG
48 | TG17 | TG17-10 |  | EN | (EN 300 422-2) REN/ERM-TG17WG3-014-1 Harmonized EN for wireless microphones in the 25 MHz to 3 GHz | Delivery to the EC | 2011-09-05 | 1.3.1 |  |  |  |  | FM51
49 | BRAN | BRAN |  | EN | (EN 301 598 ) - White Space Devices (WSD); Wireless Access Systems operating in the 470 MHz to 790 MHz frequency band; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive | Start of work | 2012-02-22 |  | Drafting Stage |  |  |  | SE43, WG FM
50 | SES MARV |  |  |  | EN 303 978 Satellite Earth Stations and Systems (SES); Harmonised EN for Earth Stations on Mobile Platforms (ESOMP) transmitting towards satellites in geostationary orbit in the band 27,5 GHz to 30,0 GHz frequency bands covering essential requirements under article 3.2 of the R&TTE Directive | Final draft |  |  | Final draft for approval |  |  |  | SE40, FM44
51 | BRAN |  |  | EN | (EN 302 567) REN/BRAN-0060008 60 GHz Multiple-Gigabit WAS/RLAN Systems; Harmonized EN covering the essential requirements of article 3.2 of the R&TTE Directive | Delivery to the EC | 2012-01-16 | [5 empty] | SE19, SE21, SE24 |  | SE21 has reviewed the document (see document SE(11)084)
52 | IST |  |  | EN | Intelligent Transport Systems (ITS); Profile standard for the physical and medium access control layer of Intelligent Transport Systems operating in the 5 GHz frequency band; | Start of work | [6 empty] | WG FM, SRD-MG, WG SE, SE24
53 | JTFEA | JTFEA-5 |  | PE | (EN 303 213-5) DEN/ERM-JTFEA-005-5 Harmonized EN for Advanced Surface Movement Guidance and Control System (A-SMGCS); Part 5 for transmitter used in multilateration equipment | Early draft | 2011-02-21 |  | Stable draft | 2011-05-15 |  | 1.1.1 | WG SE21 |  | WGSE informed, info24SE(10), related to Revision ERC REC 74-01
54 | SES |  |  |  | (EN 301 444) REN/SES-00319 HS for Land Mobile Earth Stations (LMES) operating in the 1,5 GHz and 1,6 GHz bands providing voice and/or data communications | Delivery to the EC | 2012-02-14 |  | End of Public Enquiry | 2011-06-28 |  | 1.2.1 | FM44, SE40
55 | SES |  |  |  | (EN 301 681) REN/SES-00320 HS for (Geo) Mobile Earth Stations 1,5/1,6 GHz | Delivery to the EC | 2012-11-24 |  | End of Public Enquiry | 2011-06-28 |  | 1.4.1 | FM44, SE40
56 | TG17 | TG17-11 |  |  | (EN 302 017-2) REN/ERM-TG17WG2-007-2 Transmitting equipment for the amplitude-modulated broadcast radio service | TB adoption of WI | 2010-05-28 |  | Start of work | 2010-10-15 |  |  | WG FM
57 | TG17 | TG17-11 |  |  | (EN 302 018-2) REN/ERM-TG17WG2-008-2 Frequency Modulated (FM) sound broadcasting transmitters | TB adoption of WI | 2010-05-28 |  | Start of work | 2010-10-15 |  |  | WG FM
58 | TG17 | TG17-11 |  |  | (EN 302 077-2) REN/ERM-TG17WG2-005-2 Harmonised EN for Terrrestrial Digital Audio Broadcast (TDAB) | TB adoption of WI | 2010-05-28 |  | Final draft for approval | 2011-03-15 |  |  | WG FM
59 | TG17 | TG17-11 |  |  | (EN 302 245-2) REN/ERM-TG17WG2-006-2 DRM | TB adoption of WI | 2010-05-28 |  | Start of work | 2010-10-29 | 1.2.1 |  | WG FM
60 | TG17 | TG17-11 |  |  | (EN 302 297) REN/ERM-TG17WG1-003 Analogue TV | TB adoption of WI | 2010-05-28 |  | Start of work | 2010-10-29 |  |  | WG FM
61 | TGDMR | TGDMR-11 |  |  | (EN 300 113-2) REN/ERM-TGDMR-296-2 Land mobile service; Radio equipment intended for the transmission of data (and/or speech) using constant or non-constant envelope modulation and having an antenna connector; Part 2: Harmonized EN covering essential requirements of article 3.2 of the R&TTE Directive | Start of Public Enquiry | 2011-05-06 |  | End of Public Enquiry | 2011-09-05 |  |  | WG SE, SE7
62 | TGSRR | TGSRR-8 | NWI |  | (EN 303 057-2) Short Range Radar (SRR) equipment using a WLAM Mode (Wideband Low Activity Mode) and operating in the 24,05 - 24,50 GHz range; Part 2: Harmonized European Standard covering the essential requirements under article 3.2 of the R&TTE directive. | Start of work | 2010-03-26 |  | Final draft for approval | 2011-02-14 |  |  | WG FM, SRD-MG, WG SE, SE19, SE24
SE21 activities
EN 303 213 (JTF Aero/ERM) Advanced Surface Movement Guidance and Control System (A-SMGCS);draft available – related to discussion about table 5.1 in annex 5 of ERC REC 74-01
ETSI EN 300 328 (ERM TG11) Wideband transmission systems;Data transmission equipment operating in the 2,4 GHz ISM band and using wide band modulation techniques related to table 2.1 in annex 2 of ERC REC 74-01
Note that in ERM RM - MI/ERM-RM-025 (27-10-2011) deals with An overview of the alignment of ETSI standards with CEPT/ERC Rec. 74-01 will be produced for internal-ETSI consideration. In addition recommendations to enhance the alignment may be developed for consideration by TC ERM and CEPT/ECC-WG SE.